## Slide 1
SMART-RECOVERY
Phase 1 Smart-Recovery Portal
Execution Readiness Kit & Executive Funding Briefing
PRESENTER
Technical Business Analyst / Product Delivery Team
DATE
October 2026

## Slide 2
SMART-RECOVERY
Executive Board Recommendation
RECOMMENDATION: APPROVE £130,000 PHASE 1 FUNDING IMMEDIATELY
Unlocks £1.48M Net 12-Mo. Value • Deflects 38,000 Routine Cases • Zero Legacy DB Overhaul
Focused Scope
INCLUDED CORE FEATURES
Identity & 2FA: SMS OTP verification
Account & Payment Engine: Real-time balance & schedules
P2P Capture: Binding digital commitments
Rep Workspace: Interaction history & flags
STRICT EXCLUSIONS
Bespoke negotiations, forbearance, automated legal litigation
Value & Urgency
£1.57M
GROSS ANNUAL VALUE
< 1.1 Month Payback: Rapid capital return
38,000 Cases Deflected: 38% total automated
Reclaims 2.86 Hrs/Rep/Day: Eliminates re-keying
Stops £500k/Yr Loss: Removes tracking friction
Managed Delivery Risks
DE-RISKED ARCHITECTURE
REST API Wrapper: Bypasses DB schema risk
Instant Outreach Freeze: Auto-suppresses dialer on hardship
Human Empathy Routing: Direct exception handoff
12-Sprint Delivery: 21 sized user stories

## Slide 3
Target To-Be Process Architecture & Exception Safeguards
1. CUSTOMER SELF-SERVICE SWIMLANE
2FA Authentication
DEP-04
Account Summary View
SO-01
P2P / Payment Plan Selection
Dispute & Hardship Intake
2. AUTOMATED ENGINE SWIMLANE
Set outreach_suppression
VALUE = TRUE
Sync Core DB Flags
DEP-03
3. FRONTLINE OPERATIONS SWIMLANE
Vulnerability Specialist Queue
24H SLA GUARANTEE
Manager Escalation Queue
TIER-2 REVIEW
4. COMPLIANCE & LEGAL SWIMLANE
Dispute Compliance Review
48H SLA GUARANTEE
Manager Review & Legal Handoff
AS-IS LEGAL HANDOFF
Automated Trigger
Exception / SLA Pathway
Final Compliance Exit

## Slide 4
SMART-RECOVERY
Phase 1 Backlog Sizing & Epic Distribution
21 USER STORIES TOTAL
Backlog Sizing Breakdown
PRIORITY
STORIES
POINTS
HOURS
% SCOPE
Must-Have
CRITICAL PATH
14
70
280
80.5%
Should-Have
HIGH VALUE
6
15
60
17.2%
Could-Have
DESIRABLE
1
2
8
2.3%
Total Phase 1
FULL BACKLOG
21
87
348
100%
Epic Coverage Distribution
Access & Verification
Authentication & Security Baseline
US-01 to 04
4 Stories
Account Visibility
Balance & Status Dashboards
US-05 to 09
5 Stories
P2P & Payment Plans
Core Settlement Workflows
US-10 to 13
4 Stories
Exception Routing
Edge Cases & Manual Review
US-14 to 18
5 Stories
Reporting & Audit Trail
Compliance & Analytics Export
US-19 to 21
3 Stories

## Slide 5
Technical Dependencies & System Ownership Matrix
DEPENDENCY & SYSTEM
OWNER / RISK STATUS
TECHNICAL SPECIFICATION / DESCRIPTION
DEP-01
Core DB REST API Wrapper
Owner TBC
Delivery Risk #1
Lightweight API wrapper providing read/write REST endpoints without database schema modifications.
DEP-02
Payment Gateway Integration
Owner TBC
Delivery Risk #2
Enterprise PCI-compliant payment gateway for debit card processing and Direct Debit tokenization.
DEP-03
Real-Time Ledger Status Flag Writing
Owner TBC
Delivery Risk #3
Asynchronous API parameter write-backs (dispute_flag = 1, ptp_active = 1) for manager observability.
DEP-04
Enterprise SMS / OTP Gateway
Owner TBC
Delivery Risk #4
Enterprise SMS gateway required for dynamic 6-digit 2FA authentication.

## Slide 6
SMART-RECOVERY
ADKAR Adoption Risks & Designed Phase 1 Mitigations
FRONTLINE REPS
RISK: SYSTEM BYPASS
Users bypass core system workflows, preferring manual legacy workarounds.
PHASE 1 MITIGATION
Rep Interaction History Workspace (US-07): Unified single-pane workspace.
Eliminates Manual Re-keying: Saves 2.86 hrs/day/rep by removing spreadsheet redundancy.
DELINQUENT CUSTOMERS
RISK: BRITTLE UX ABANDONMENT
Complex portal authentication and payment flows drive high drop-off rates.
PHASE 1 MITIGATION
Frictionless 2FA Login (US-01): Streamlined identity verification.
3 Pre-Calculated Installments (US-10): Simplified self-service resolution options.
60-s SMS Dispatches (US-13): Instant automated confirmations.
OPERATIONS LEADERSHIP
RISK: OBSERVABILITY GAP
Lack of real-time operational oversight across core settlement ledgers.
PHASE 1 MITIGATION
Real-Time Core Ledger Flags (DEP-03): Immediate status updates on transaction states.
TL Manager Dashboards (US-23): Dedicated observability suite for team leads.